## Sheet1
| Project name | Project duration | Start date | End date
| Tic Tac Toe Project |  | 2022-06-14 | 2022-07-12
Task ID | Task Description | Task Duration | Start date | End date | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12
1 | Milestone 1 | 15 | 2022-06-14 | 2022-06-29 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| Defining and understanding the problem | 15 | 2022-06-14 | 2022-06-29
2 | Time management plan writup | 5 | 2022-06-14 | 2022-06-19 | X | X | X | X | X | X
3 | Create Gantt chart | 4 | 2022-06-14 | 2022-06-18 | X | X | X | X | X
4 | Program description/overview | 4 | 2022-06-17 | 2022-06-21 |  |  |  | X | X | X | X | X
5 | Functional requirments | 6 | 2022-06-19 | 2022-06-25 | [5 empty] | X | X | X | X | X | X | X
6 | Context diagram | 2 | 2022-06-26 | 2022-06-28 | [12 empty] | X | X | X
7 |  | 3 | 17 | 1900-01-19
8 | Milstone 2 | 36 | 2022-06-30 | 2022-08-05 | [16 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Planning and designing software solutions
9 | System models |  |  | 0
10 | Dataflow diagram |  |  | 0
11 | Structure diagram |  |  | 0
12 | IPO chart for subprogram |  |  | 0
| Screen design |  |  | 0
| Storyboard |  |  | 0
| Complete pseudocode |  |  | 0
| Flow chart for subprogram |  |  | 0
| Implementing software solutions |  |  | 0
0
0
0
13 |  |  |  | 0
14 | Milestone 3 | 6 | 2022-08-06 | 2022-08-12 | [53 empty] | X | X | X | X | X | X | X
15 |  |  |  | 0
16 |  |  |  | 0
17 |  |  |  | 0
18 |  |  |  | 0
19 |  |  |  | 0
20 |  |  |  | 0
21 |  |  |  | 0
22 | Logbook | 59 | 2022-06-14 | 2022-08-12 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Formulas:
End date = [Start date] + [Project duration]